## Pre-requite
Steps | Pre-requite
1 | Create the Main Repository
2 | Push the Initial Project Solution to the Main Branch
3 | Create a Child Release or UAT Branch from Main
4 | Create a Child Dev Branch from Release or UAT Branch
5 | Set Up Permissions and Restrict Access to Critical Branches (Main and Release).

## Deployment Process
Power App Dev Environment | [9 empty] | Power App Test/Uat/Stg/Main Environment
Developer Responsibility
User Branch
SP1 - Day1 to Day3 | Fetch the code from the SP1 branch into the User branch.
|  | Perform development tasks to build and implement the required features or functionalities. | Soln pushed to Dev Environment
Deploy the .dll or JavaScript in Dev Environment using PRT or the Dev Tool.
Perform unit testing to validate the functionality of individual components or methods.
Commit the code changes to the User branch.
Create a pull request to merge changes into the SP1 branch.
Tech Lead Responsibility
SP1 Branch
SP1 - Day4 to Day6 | [6 empty] | Approve the code and merge it into the SP1 branch. | Updated code Pushed to SP Branch
Create a pull request to merge changes from the SP1 branch into the Dev branch.
Tech Lead Responsibility
Dev Branch
SP1 - Day7 | [8 empty] | Approve the code, merge it into the Dev branch, run the build pipeline, export the unmanaged solution from the Dev environment, and save it to Git. | Updated code moved to Dev Branch
Create a pull request to merge changes from the Dev branch into the Release/UAT branch.
[11 empty] | Tech Lead Responsibility | Dev Ops Developer Responsibility | Tester Responsibility
Test/Stg/Uat Branch
SP1 - Day8 to Day9 | [10 empty] | Approve the code and merge it into the Release/UAT branch.Run the build pipeline, export the unmanaged solution from the environment, and save it to Git. | Updated code moved to higher branch ( Test/UAT/Staging)
[12 empty] | Deploy Manage Solution in Test/Uat/Stg using Azure DevOps CI/CD pipeline. | Solution pushed to higher Environment
Execute unit tests to ensure the functionality of individual components is working as expected.
Create a pull request to merge changes from the Release/Uat branch into the Main branch.
Main
[15 empty] | Approve the code and merge it into the Main branch.Run the build pipeline, export the unmanaged solution from the environment, and save it to Git. | Final code moved to Main Branch
[14 empty] | Deploy Manage Solution in Prod Envronment using Azure DevOps CI/CD pipeline From Release/Uat Branch. | Managed Solution deplyed into Prod